## Activities
Activity Name | Type | Week | Responsible | Estimated Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 3
Complete Process Grid | Preparation | 3 | Steven | 2 | 1 | Done |  | 1 | 100
Submit Activity Tracker | Documentation | 3 | Andrew | 1 | 1 | Done |  | 0 | 0
Post Status Report to Blog | Documentation | 3 | Alejandro | 1 | 1 | Done |  | 0 | 0
Done
Done
Done
Done
Done
Done
Done
Done
Week 4
Complete Use Case | Design | 4 | Andrew | 2 | 2 | Done |  | 0 | 0
Complete Use Case | Design | 4 | Steven | 2 | 2 | Done |  | 0 | 0
Complete Use Case | Design | 4 | Alejandro | 2 | 2 | Done |  | 0 | 0
Complete Use Case | Design | 4 | Connor | 2 | 3 | Done |  | -1 | 33.3333
Complete Use Case | Design | 4 | Peter | 3 | 3 | Done |  | 0 | 0
Complete Use Case | Design | 4 | Kiem | 3 | 3 | Done |  | 0 | 0
Done
Done
Done
Done
Week 5
Complete SRS Documentation | Documentation | 5 | Andrew | 2 | 1.5 | Done |  | 0.5 | 33.3333
Complete SRS Documentation | Documentation | 5 | Steven | 2 | 2 | Done |  | 0 | 0
Complete SRS Documentation | Documentation | 5 | Alejandro | 2 | 2 | Done |  | 0 | 0
Complete SRS Documentation | Documentation | 5 | Connor | 2 | 2.5 | Done |  | -0.5 | 20
Complete SRS Documentation | Documentation | 5 | Peter | 2 | 1.5 | Done |  | 0.5 | 33.3333
Complete SRS Documentation | Documentation | 5 | Kiem | 2 | 2 | Done |  | 0 | 0
Done
Week 6
Worked on project design | Design | 6 | Andrew | 3 | 2.5 | Done |  | 0.5 | 20
Worked on project design | Design | 6 | Steven | 3 | 2.7 | Done |  | 0.3 | 11.1111
Worked on project design | Design | 6 | Alejandro | 3 | 2.4 | Done |  | 0.6 | 25
Worked on project design | Design | 6 | Connor | 3 | 2.8 | Done |  | 0.2 | 7.1429
Worked on project design | Design | 6 | Peter | 3 | 2.5 | Done |  | 0.5 | 20
Worked on project design | Design | 6 | Kiem | 3 | 2.4 | Done |  | 0.6 | 25
Done
Done
Week 7
Complete Project design | Design | 7 | Andrew | 4 | 3.3 | Done |  | 0.7 | 21.2121
Complete Project design | Design | 7 | Steven | 4 | 3.6 | Done |  | 0.4 | 11.1111
Complete Project design | Design | 7 | Alejandro | 4 | 3.8 | Done |  | 0.2 | 5.2632
Complete Project design | Design | 7 | Connor | 4 | 3.5 | Done |  | 0.5 | 14.2857
Complete Project design | Design | 7 | Peter | 4 | 3.6 | Done |  | 0.4 | 11.1111
Complete Project design | Design | 7 | Kiem | 4 | 3.7 | Done |  | 0.3 | 8.1081
Done
Done
Done
Done
Week 8
Work on PHP file to obtain lots | Development | 8 | Andrew | 5 | 3 | Done |  | 2 | 66.6667
Work on GUI | Interfaces | 8 | Steven | 5 | 6 | Done |  | -1 | 16.6667
Work on GUI | Interfaces | 8 | Alejandro | 5 | 5 | Done |  | 0 | 0
Research Google API, implement | Development | 8 | Connor | 5 | 5 | Done |  | 0 | 0
Work on PHP file to obtain permits | Development | 8 | Peter | 5 | 2.5 | Done |  | 2.5 | 100
Work on PHP file to obtain Campus | Development | 8 | Kiem | 5 | 2.6 | Done |  | 2.4 | 92.3077
Done
Done
Week 9
Work on PHP file to obtain lots | Development | 9 | Andrew | 5 | 4 | Done |  | 1 | 25
Work on GUI | Interfaces | 9 | Steven | 5 | 5 | Done |  | 0 | 0
Work on GUI | Interfaces | 9 | Alejandro | 5 | 5 | Done |  | 0 | 0
Research Google API, implement | Development | 9 | Connor | 5 | 5 | Done |  | 0 | 0
Work on PHP file to obtain permits | Development | 9 | Peter | 5 | 4 | Done |  | 1 | 25
Work on PHP file to obtain Campus | Development | 9 | Kiem | 5 | 5 | Done |  | 0 | 0
Done
Done
Done
Done
Done
Done
Done
Done
Week 10
Complete test plan | Testing | 10 | Andrew | 2 | 2 | Done |  | 0 | 0
Complete test plan | Testing | 10 | Steven | 2 | 1.6 | Done |  | 0.4 | 25
Complete test plan | Testing | 10 | Alejandro | 2 | 2 | Done |  | 0 | 0
Complete test plan | Testing | 10 | Connor | 2 | 1.5 | Done |  | 0.5 | 33.3333
Complete test plan | Testing | 10 | Peter | 2 | 1.6 | Done |  | 0.4 | 25
Complete test plan | Testing | 10 | Kiem | 2 | 1.5 | Done |  | 0.5 | 33.3333
Done
Done
Done
Done
Done
[6 empty] | Done |  | 1 | 25
Done
Done
Done
Week 11
Work on PHP - lots | Development | 11 | Andrew | 5 | 4 | Done |  | 1 | 25
Stream line GUI | Interfaces | 11 | Steven | 5 | 4 | Done |  | 1 | 25
Stream line GUI | Interfaces | 11 | Alejandro | 5 | 4 | Done |  | 1 | 25
Troubleshoot Google API | Development | 11 | Connor | 5 | 4 | Done |  | 1 | 25
Work on PHP- permits | Development | 11 | Peter | 5 | 4 | Done |  | 1 | 25
Work on PHP - Campus | Development | 11 | Kiem | 5 | 4 | Done |  | 1 | 25
Done
Done
Done
Done
Done
Done
Week 12
Work on finalizing project | Development | 12 | Andrew | 6 | 6 | Done |  | 0 | 0
Work on finalizing project | Development | 12 | Steven | 6 | 6 | Done
Work on finalizing project | Development | 12 | Alejandro | 6 | 6 | Done |  | 0 | 0
Work on finalizing project | Development | 12 | Connor | 6 | 6 | Done |  | 0 | 0
Work on finalizing project | Development | 12 | Peter | 6 | 6 | Done |  | 0 | 0
Work on finalizing project | Development | 12 | Kiem | 6 | 6 | Done |  | 0 | 0
Note on C1: swami: This is useful for generating subtotals and reports
Note on D1: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on H1: swami: Insert your own comments
Note on I1: SE: This field is updated automatically

## Reports
The charts here update automatically

## SummaryData
Note: All data on this sheet updated automatically
Item |  | Week |  | Total Estimation Error % | Count | Average Estimation Error %
Criteria
Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
EstimationError
Week1 |  | 1 |  | 0 | 0 | 0
Week2 |  | 2 |  | 0 | 0 | 0
Week3 |  | 3 |  | 100 | 3 | 33.3333
Week4 |  | 4 |  | 33.3333 | 6 | 5.5556
Week5 |  | 5 |  | 86.6667 | 6 | 14.4444
Week6 |  | 6 |  | 108.254 | 6 | 18.0423
Week7 |  | 7 |  | 71.0913 | 6 | 11.8486
Week8 |  | 8 |  | 275.641 | 6 | 45.9402
Week9 |  | 9 |  | 50 | 6 | 8.3333
Week10 |  | 10 |  | 116.6667 | 6 | 19.4444
Activity |  |  |  |  | Actual Effort
Requirements |  |  |  |  | 0
Design |  |  |  |  | 51.8
Development |  |  |  |  | 83.1
Testing |  |  |  |  | 10.2
Interfaces |  |  |  |  | 29
Documentation |  |  |  |  | 13.5
Coordination |  |  |  |  | 0
Preparation |  |  |  |  | 1
Delivery |  |  |  |  | 0
Criteria
Type | Type | Type | Type | Type | Type | Type | Type | Type
Requirements | Design | Development | Testing | Interfaces | Documentation | Coordination | Preparation | Delivery
EstimationError |  | Total | Count | Average
Requirements |  | 0 | 0 | 0
Design |  | 212.6786 | 18 | 11.8155
Development |  | 408.9744 | 17 | 24.0573
Testing |  | 116.6667 | 6 | 19.4444
Interfaces |  | 66.6667 | 6 | 11.1111
Documentation |  | 86.6667 | 8 | 10.8333
Coordination |  | 0 | 0 | 0
Preparation |  | 100 | 1 | 100
Delivery |  | 0 | 0 | 0
Week-wise-Effort
Week1 |  | 1 |  |  | 0
Week2 |  | 2 |  |  | 0
Week3 |  | 3 |  |  | 3
Week4 |  | 4 |  |  | 15
Week5 |  | 5 |  |  | 11.5
Week6 |  | 6 |  |  | 15.3
Week7 |  | 7 |  |  | 21.5
Week8 |  | 8 |  |  | 24.1
Week9 |  | 9 |  |  | 28
Week10 |  | 10 |  |  | 10.2
Total effort |  |  |  |  | 128.6

## Instructions
Using the activity tracker
At the end of each week, update the status of all activities completed during the week
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
After each release, look at the "reports" section to see charts of how much time has been spent so far, and what activities it has been spent on
Use the charts and data to identify needs for improvement